## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2022-02-15 |  |  |  |  | April | [27 empty] | May
Scrolling Increment: | 53 | time axis 2022-04-09 to 2022-06-03
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-04-09 to 2022-06-03
Iteration 1
Complete all products for Iteration 1 | Goal | Sass, Elisa | 100% | 2022-03-01 | 21
Iteration 1 Project Planning and Meeting Minutes | Low Risk | Elisa | 100% | 2022-03-01 | 1
Complete Stakeholder Register | High Risk | Sass | 100% | 2022-03-01 | 7
Design Personas - three | Med Risk | Sass | 100% | 2022-03-02 | 13
Submit Progress Report 1 | On Track | Elisa, Sass | 100% | 2022-03-15 | 1
Review Personas - three | Med Risk | Elisa | 100% | 2022-03-15 | 6
ITERATION 1 COMPLETED | Milestone | Elisa, Sass | 100% | 2022-03-21 | 1
Iteration 2
Complete all products for Iteration 2 | Goal | Elisa, Sass | 100% | 2022-03-22 | 21 | 2022-04-09: 2; 2022-04-10: 2; 2022-04-11: 2
Iteration 2 Project Planning and Meeting Minutes | Low Risk | Elisa, Sass | 100% | 2022-03-22 | 1
Create Gantt Chart | Low Risk | Sass | 100% | 2022-03-23 | 22
Create Resource Requirements List | Med Risk | Elisa | 100% | 2022-03-25 | 7
Submit Progress Report 2 | On Track | Elisa, Sass | 100% | 2022-04-12 | 1
ITERATION 2 COMPLETED | Milestone | Elisa, Sass | 100% | 2022-04-12 | 1 | bar: 2022-04-12
Iteration 3
Complete all products for Iteration 3 | Goal | Elisa, Sass | 100% | 2022-05-03 | 28 | 2022-05-03: 2; 2022-05-04: 2; 2022-05-05: 2; 2022-05-06: 2; 2022-05-07: 2; 2022-05-08: 2; 2022-05-09: 2; 2022-05-10: 2; 2022-05-11: 2; 2022-05-12: 2; 2022-05-13: 2; 2022-05-14: 2; 2022-05-15: 2; 2022-05-16: 2; 2022-05-17: 2; 2022-05-18: 2; 2022-05-19: 2; 2022-05-20: 2; 2022-05-21: 2; 2022-05-22: 2; 2022-05-23: 2; 2022-05-24: 2; 2022-05-25: 2; 2022-05-26: 2; 2022-05-27: 2; 2022-05-28: 2; 2022-05-29: 2; 2022-05-30: 2
Iteration 3 Project Planning and Meeting Minutes | Low Risk | Elisa, Sass | 100% | 2022-05-03 | 1
Create Risk Register | Low Risk | Sass | 100% | 2022-05-03 | 12
User Acceptance Test Results Template | High Risk | Elisa | 100% | 2022-05-24 | 4
Submit Progress Report 3 | On Track | Elisa, Sass | 100% | 2022-05-24 | 1
ITERATION 3 COMPLETED | Milestone | Elisa, Sass | 100% | 2022-05-30 | 1 | bar: 2022-05-30
TITLE 4
Task 1 |  |  |  | 2022-05-27 | 0
Task 2 |  |  |  | 2022-06-10 | 0
Task 3 | Milestone |  |  | 2022-07-22 | 0
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2022-05-25 |  |  |  |  | May | [6 empty] | June | [34 empty] | July
Scrolling Increment: | 1 | time axis 2022-05-26 to 2022-07-20
Milestone description | Category | Assigned to | Progress | Start | Days | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
TITLE 1
Task 1 | Goal | Name | 25% | 2022-05-25 | 3 | T: 2; F: 2
Task 2 | Milestone |  |  | 2022-05-30 | 1 | bar: M
Task 3 | Low Risk |  | 50% | 2022-05-22 | 10
Task 4 | Milestone |  |  | 2022-06-14 | 1 | bar: T
Task 5 | Med Risk |  | 10% | 2022-05-31 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2022-05-31 | 13
Task 2 | On Track |  | 50% | 2022-06-02 | 9
Task 3 | Low Risk |  | 33% | 2022-06-07 | 11
Task 4 | Milestone |  |  | 2022-06-09 | 1 | bar: T
Task 5 |  |  |  | 2022-06-10 | 24
TITLE 3
Task 1 | On Track |  |  | 2022-06-09 | 4
Task 2 | Med Risk |  |  | 2022-06-12 | 14
Task 3 | On Track |  |  | 2022-06-27 | 6
Task 4 | Goal |  |  | 2022-07-01 | 3 | F: 2; S: 2; S: 2
Task 5 | Low Risk |  |  | 2022-05-31 | 19
TITLE 4
Task 1 |  |  |  | 2022-07-04 | 15
Task 2 |  |  |  | 2022-07-18 | 5
Task 3 | Milestone |  |  | 2022-08-29 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2022-05-25 |  |  |  |  | May | [6 empty] | June | [27 empty] | July
Scrolling Increment: | 5 | time axis 2022-05-30 to 2022-07-24
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-05-30 to 2022-07-24
TITLE 1
Task 1 | Goal | Name | 25% | 2022-05-25 | 3
Task 2 | Milestone |  |  | 2022-05-30 | 1 | bar: 2022-05-30
Task 3 | Low Risk |  | 50% | 2022-05-22 | 10
Task 4 | Milestone |  |  | 2022-06-14 | 1 | bar: 2022-06-14
Task 5 | Med Risk |  | 10% | 2022-05-31 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2022-05-31 | 13
Task 2 | On Track |  | 50% | 2022-06-02 | 9
Task 3 | Low Risk |  | 33% | 2022-06-07 | 11
Task 4 | Milestone |  |  | 2022-06-09 | 1 | bar: 2022-06-09
Task 5 |  |  |  | 2022-06-10 | 24
TITLE 3
Task 1 | On Track |  |  | 2022-06-09 | 4
Task 2 | Med Risk |  |  | 2022-06-12 | 14
Task 3 | On Track |  |  | 2022-06-27 | 6
Task 4 | Goal |  |  | 2022-07-01 | 3 | 2022-07-01: 2; 2022-07-02: 2; 2022-07-03: 2
Task 5 | Low Risk |  |  | 2022-05-31 | 19
TITLE 4
Task 1 |  |  |  | 2022-07-04 | 15
Task 2 |  |  |  | 2022-07-18 | 5
Task 3 | Milestone |  |  | 2022-08-29 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one